## Capital Summary Worksheet
Capital Project Worksheet
Forest View Acres Water District |  | ON-GOING WORKSHEET
Area of Improvement |  |  | Priority Ranking Sheet 2 for Cash Flow Priority 1 Items | Capital Cost | Description/Project value | Concerns | Other Comments
| Facility |  |  | Very Rough Costs
|  | Project |  | in 2020 dollars
Surface Water Source | Surface Water Plant
| Short Term | Fix Filters/Media | DONE | 5000
|  | Possibly replace one primary filter | 3 | 30000 | Replacing the primary filter is not an immediate need but certain other fixes to the secondarys are immediate need. Vessel cost is approx $13,500 but installation and removal/diposal of existing vessel would also be required.
|  | Backwash to Primary with Raw | 2 |  | Consider Replacing Clean Water Backwash with Raw--must be primary filters only
| Long Term | Full Plant Replacement |  | 1500000 |  | Plant is aging substantially | We have not delved deeply into styles or plant types. There are numerous options but we continue to currently lean to more traditional treatment which lends itself to a wider variety of influent turbidities
|  |  | 2 |  | Water is renewable/Excellent long term quality. Water is most water/power efficient | Borderline vs current standards
Getting increasingly unreliable
This must be considered a < 5 year need
| Intake Equalization |  | 2 | 280000 | Increases Efficiency of SWTP during times of lower flows | Helps with operation, does not extend life of basic plant
Important to make this work or convertible to new plant
[5 empty] | Requires significant legal and engineering work to obtain water rights | Outcome a bit uncertain
| Alluvial Water Well | Long Term Project |  | Soft Costs
| (not really Capital at this time) | First efforts probably soft costs | Unranked | 150000 | Could produce 80 to 90 % of Arapahoe Input
Legal and Engineering
|  | Replace all or portions of this line, this could be phased |  | 2000000 | This is critical to delivering the raw water to surface plant | Freezing problems
| Raw Water Delivery/Pipeline |  |  |  |  | Compentency problems
|  |  | 3 |  |  | Size issues
Exteremely expensive and difficult to replace
Denver Basin Source |  | Priority 1 Arap Plant Upgrades | 1 | 30000 | Instrumentation and Control Modifications: Water On Floor Monitor, Internet and New Dialer to Allow Remote Access to Set Points | Aging plant
| Arapahoe Plant |  |  | 5000 | Second Booster Pump added for redundancy | Long Term Radium Issues
|  |  |  | 2000 | Seal Existing Building Wall Penetrations
|  | Priority 2 Arap Plant Upgrades | 2 | 1000 | Paint Building | Water Availability/Reliability is predictable | New Regulatory Requirements: Issues related to TENORM will arise in late 2021
|  |  |  | 10000 | Site Drainage Improvements - Grading, Gravel and Culvert
|  |  |  | 2000 | Replace/Repair Garage Door
|  |  |  | 2000 | Replace Heater in Office Space
|  |  |  | 25000 | Switch Filter Backwash to Fresh Water
Done
| Arapahoe Well Install New Pump | Pump Install | Done
[5 empty] | Partially overlaps A Plant issues | Water Availability is predictable | New Regulatory Requirements: Issues related to TENORM will arise in late 2021
| Dawson Well/Delivery | Implement Dawson Well | 1 | 750000 | Requires certain improvements in A plant | Long Term Radium Issues
Uncertainties in required treatment
Distribution and Other System Elements |  |  |  | 70000 | Does not include any cost for land easements | This project is generally required to replace a facility that is inadequate and does not have adequate legal authority for placement and operation. | Portions of this effort are hoped to be aided by the adjacent homeowner who needs service. Some horsetrading may benefit
| Clovenhoof Easement/ Pipeline | Six Inch Line | 1 | to $150,000 | This remains a bit of an unknown until we dig into certain issues. There is a probably a minimum of 450 feet of pipe and easement with another 750 feet of maybe.
|  | Develop mutual aid Interconnect between FVAWD and Town of Palmer Lake and/or Town of Monument |  |  | This is not a new source | Requires easement ROW ??? | A temporary connection can be implemented with Palmer Lake, but lacks good operation characteristics. This would be a fire hydrant above ground fire line coming into Booster Station. We have no hydraulics or other info on Monument
| System Interconnects |  | 2 | 150000 | Consider Mutual Aid Connection Agreement
Town of Monument on lower side of system. No cost shown
| Distribution Facilities |  |  | Clovenhoof ($18,000) | Distribution replacements sometimes are opportunity driven and sometimes are third party conditions driven. One option is to fund these types of replacments is to allocate annual budgets. One common intent is to budget say $50,000/year |  | Funding of $50,000/year (to be accumulated) could finance 250 feet of pipe per year. Even though a short 250 foot run might be too small a project, unless need driven, this also acocunts for Valve and PRV work.
| Shiloh PRV |  | 3
Distribution Replacement/Repair
| SCADA ??? | [5 empty] | SCADA is an ongoing element. Most projects have some SCADA involved if/when there is a mechanical element involved
We do not have a specific project for SCADA.
| Potable Water Storage | Recoating |  |  | Interior and exterior recoat | Existing Tank is currently adequate, but coating replacement is in near future maybe +/- 5 years.
|  |  | 2 | 190000
This is a non-specific project. Although many lines in FVAWD have been replaced, others are yet in need. This is not associated with any particular segment.
| Six Inch Line Replacement (1500 Feet) |  | 2 | 262500
1 | Immediate | Capital; |  | These are generally projects that expand capacity and or meet an expended regulatory need. Replacements when considered capital are generally global or at least regional in nature. Typically replacement of an aging pipeline /pump is considered R/R.
2 | Needed <5 years
3 | 5 years and beyond | [5 empty] | JDS-Hydro Consultants, Inc
225000
300000

## Priority 1 Cash
Possible Rough Cash Flow Estimates--
Priority One Projects | 2021 |  |  |  | 2022 |  |  |  | Check Totals
| Qtr | Qtr | Qtr | Qtr | Qtr | Qtr | Qtr | Qtr | Line Total | Project Total
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Arapahoe Well Pump Relacement | [8 empty] | 0
0
Palmer Lake Sewer Adjustment
Easement ??? | [8 empty] | 0
Soft Costs Engineering/legal/negotiation | 1: 7500; 3: 2500 | 10000
Implementation Timeline Very Uncertain | 3: 60000; 4: 60000; 1: 20000 | 140000
150000
Arapahoe Plant Priority 1 Improvements | 2: 37000 | 37000 | 37000
Dawson Well/Delivery |  | 12000 | 10000 | 35000 | 7500 | 7500 | 7500 |  | 79500 | 79500
| 4: 70000; 1: 250000; 2: 300000; 3: 60000 | 680000 | 680000
0
0
0
Totals | 7500 | 49000 | 72500 | 165000 | 277500 | 307500 | 67500 | 0 | 946500 | 946500
Soft Costs
Hard Costs